## JIRA
Sprint | Issue Type | Issue key | Summary | Priority | Status | Description | Outward issue link (Blocks) | Outward issue link (Blocks) | Assignee | Original Estimate | Remaining Estimate
turtlebot_rrt 1 | Task | TR-47 | Set up Travis CI | Medium | In Progress | Add github repository to Travis-CI (https://travis-ci.org/jeshoward/turtlebot_rrt) Add Travis badge to README |  |  | Jessica Howard | 900 | 900
turtlebot_rrt 1 | Task | TR-46 | Add license to GITHUB | Medium | Done | BSD 3-clause license |  |  | Jessica Howard | 900 | 900
turtlebot_rrt 1 | Sub-task | TR-36 | Relationship diagram for publishers and subscribers | Medium | To Do | Create a diagram to show how the RRT path planner interacts with other topics and the navigation stack | TR-4 |  | Jessica Howard | 1800 | 1800
turtlebot_rrt 1 | Sub-task | TR-35 | Activity diagram for obstacle avoidance | Medium | To Do | Create an activity diagram to show how the RRT path planner deals with obstacles and avoids them. | TR-4 |  | Jessica Howard | 2700 | 2700
turtlebot_rrt 1 | Sub-task | TR-34 | Activity diagram for RRT algorithm | High | In Progress | Create an activity diagram to show the basic flow of the RRT path planning algorithm | TR-4 |  | Jessica Howard | 3600 | 1800
turtlebot_rrt 1 | Sub-task | TR-33 | Class diagram for RRT_Planner | High | In Progress | Create a class diagram for the RRT_Planner plugin | TR-4 |  | Jessica Howard | 3600 | 3600
turtlebot_rrt 1 | Task | TR-32 | Create UML diagrams | Medium | In Progress | Perform any final edits and cleaning up of UML diagrams described in subtasks Upload to github/UML/initial or github/UML/revised | TR-4 |  | Jessica Howard | 3600 | 3600
turtlebot_rrt 1 | Sub-task | TR-31 | README Testing Instructions | Medium | In Progress | For sprint 1 write stub in README for testing instructions For sprint 2 fill out stub completely | TR-4 | TR-43 | Jessica Howard | 2700 | 2700
turtlebot_rrt 1 | Sub-task | TR-30 | README Dependencies | Medium | In Progress | For sprint 1 write a stub on the dependencies For sprint 2 complete dependency list in README, complete install instructions in docs/README_DEPENDENCIES | TR-4 |  | Jessica Howard | 2700 | 2700
turtlebot_rrt 1 | Sub-task | TR-29 | README Run Steps | Medium | In Progress | Sprint 1: Write stub for demo test steps, usage Sprint 2: Complete demo test steps, usage | TR-4 |  | Jessica Howard | 900 | 900
turtlebot_rrt 1 | Sub-task | TR-28 | README Build Steps | Medium | Done | Instructions for cloning the repository and building it | TR-4 |  | Jessica Howard | 900 | 0
turtlebot_rrt 1 | Sub-task | TR-27 | README Install Instructions | Medium | Done | Instructions for installation in README Instructions for dependencies in docs/README_DEPENDENCIES | TR-4 |  | Jessica Howard | 900 | 0
turtlebot_rrt 1 | Sub-task | TR-26 | README Overview | Medium | Done | Overview of the project including a blurb about me | TR-4 |  | Jessica Howard | 1800 | 600
turtlebot_rrt 1 | Task | TR-25 | Write README | Medium | In Progress | Sprint 1: Polish, make sure all stubs are in place, all links work. Sprint 2: Make sure that all stubs are completely filled out, spell check, link check. | TR-4 |  | Jessica Howard | 7200 | 7200
turtlebot_rrt 2 | Task | TR-48 | Unit Test Stubs | Medium | To Do |  |  |  | Jessica Howard
turtlebot_rrt 2 | Sub-task | TR-45 | Fix cpplint errors | Medium | To Do |  |  |  | Jessica Howard | 3600 | 3600
turtlebot_rrt 2 | Sub-task | TR-44 | Fix cppcheck errors | Medium | To Do |  |  |  | Jessica Howard | 3600 | 3600
turtlebot_rrt 2 | Task | TR-43 | Unit Testing | Medium | To Do |  |  |  | Jessica Howard
turtlebot_rrt 2 | Task | TR-42 | Write smooth path traversal algorithm | Medium | To Do |  |  |  | Jessica Howard | 7200 | 7200
turtlebot_rrt 2 | Task | TR-41 | Implement PID Controller | Medium | To Do |  |  |  | Jessica Howard | 3600 | 3600
turtlebot_rrt 2 | Task | TR-40 | Write safe path checking algorithm | Medium | To Do |  |  |  | Jessica Howard | 3600 | 3600
turtlebot_rrt 2 | Task | TR-39 | Write obstacle avoidance algorithm | Medium | To Do |  |  |  | Jessica Howard | 7200 | 7200
turtlebot_rrt 2 | Task | TR-38 | Write RRT algorithm | Medium | To Do |  |  |  | Jessica Howard | 10800 | 10800
turtlebot_rrt 2 | Task | TR-24 | Generate doxygen documentation | Medium | To Do |  |  |  | Jessica Howard | 900 | 900
turtlebot_rrt 2 | Sub-task | TR-23 | Style check loops | Medium | To Do |  |  |  | Jessica Howard
turtlebot_rrt 2 | Sub-task | TR-22 | Style check variable names | Medium | To Do |  |  |  | Jessica Howard
turtlebot_rrt 2 | Sub-task | TR-21 | Style check function names | Medium | To Do |  |  |  | Jessica Howard
turtlebot_rrt 2 | Sub-task | TR-20 | Style check file names | Medium | To Do |  |  |  | Jessica Howard
turtlebot_rrt 2 | Task | TR-19 | Google C++ style check code | Medium | To Do |  |  |  | Jessica Howard | 3600 | 3600
turtlebot_rrt 2 | Task | TR-18 | Comment code | Medium | To Do |  | TR-4 |  | Jessica Howard | 2700 | 2700
turtlebot_rrt 2 | Task | TR-17 | Run cpplint | Medium | To Do |  |  |  | Jessica Howard
turtlebot_rrt 2 | Task | TR-16 | Run cppcheck | Medium | To Do |  |  |  | Jessica Howard
turtlebot_rrt 2 | Sub-task | TR-15 | Unit test to check that max iterations are obeyed | Medium | To Do |  | TR-5 | TR-43 | Jessica Howard
turtlebot_rrt 2 | Sub-task | TR-14 | Unit test to check that shortest path is chosen | Medium | To Do |  | TR-5 | TR-43 | Jessica Howard
turtlebot_rrt 2 | Sub-task | TR-13 | Unit test for paths that traverse closely to obstacles | Medium | To Do |  | TR-5 | TR-43 | Jessica Howard
turtlebot_rrt 2 | Sub-task | TR-12 | Unit test to check paths that traverse through an obstacle | Medium | To Do |  | TR-5 | TR-43 | Jessica Howard
turtlebot_rrt 2 | Sub-task | TR-11 | Unit test for unreachable goal | Medium | To Do |  | TR-5 | TR-43 | Jessica Howard
turtlebot_rrt 2 | Sub-task | TR-10 | Unit test for goal inside an obstacle | Medium | To Do |  | TR-5 | TR-43 | Jessica Howard
turtlebot_rrt 2 | Task | TR-9 | Develop unit tests for edge avoidance | Medium | To Do |  | TR-5 | TR-43 | Jessica Howard | 1800 | 1800
turtlebot_rrt 2 | Task | TR-8 | Develop unit tests for multiple path planning | Medium | To Do |  | TR-5 | TR-43 | Jessica Howard | 7200 | 7200
turtlebot_rrt 2 | Task | TR-7 | Develop unit tests for single path planning | Medium | To Do |  | TR-5 | TR-43 | Jessica Howard | 3600 | 3600
turtlebot_rrt 2 | Task | TR-6 | Develop unit tests for obstacle avoidance | Medium | To Do |  | TR-5 | TR-43 | Jessica Howard | 7200 | 7200
turtlebot_rrt 2 | Story | TR-5 | As a user, I want to know that my robot is operating correctly. | Medium | To Do |  |  |  | Jessica Howard
turtlebot_rrt 2 | Story | TR-4 | As a user, I want to know how to operate my robot. | Medium | To Do |  |  |  | Jessica Howard
turtlebot_rrt 2 | Story | TR-3 | As a user, I can pick the map my robot will use. | Medium | To Do |  |  |  | Jessica Howard
turtlebot_rrt 2 | Story | TR-2 | As a user, I can decide how many potential paths to find. | Medium | To Do |  |  |  | Jessica Howard
turtlebot_rrt 2 | Story | TR-1 | As a user, I can tell my robot where to go. | Medium | To Do |  |  |  | Jessica Howard
turtlebot_rrt 3 | Task | TR-37 | Create demo video | Medium | To Do |  |  |  | Jessica Howard | 10800 | 3600